## Products-1748792101
Organizational Code | Program | 2024 annual plan | 12 month actual spending
56 13 09 | Tbilisi Metro Modernization Project | 5,000 | - | 0%
31 06 05 | Program for Supporting the Development of Irrigated Agliculture in Georgia (ADB, AFD, EIB) | 725 | 15 | 2%
27 04 02 02 | Rapid response project against COVID-19 (AIIB, KfW, WB) | 9,000 | 274 | 3%
25 04 04 | Kutaisi Wastewater Project (EIB, EPTATF) | 9,800 | 497 | 5%
56 13 08 | Municipal infrastructure of Batumi (Phase V) (KfW) | 10,000 | 1,495 | 15%
24 14 01 02 | Namakhvani-Tvishi-Lajanuri OHL (EBRD, KfW) | 10,500 | 1,665 | 16%
24 14 01 06 | Kheledula-Lajanuri-Oni (KfW) | 13,000 | 3,809 | 29%
56 13 02 01 | Tbilisi Solid Waste Management Project (EBRD) | 10,000 | 3,698 | 37%
24 19 | Vardnili and Enguri hydropower plants rehabilitation project (EBRD, EIB, EU) | 5,000 | 2,103 | 42%
24 14 01 01 | 500 kV OHL "Tskaltubo-Akhaltsikhe-Tortum" (KfW) | 35,000 | 17,147 | 49%
25 02 03 13 | Kakheti Transport Links Improvement Project (WB) | 90,000 | 47,083 | 52%
56 13 03 | Adjara Villages Water Supply and Wastewater Program, Georgia (EU, KfW) | 13,000 | 6,847 | 53%
25 03 03 | Regional Development Project III (Mtskheta-Mtianeti and Samtskhe-Javakheti) (WB) | 24,000 | 16,008 | 67%
24 07 02 03 - 56 13 06 | Project for Assistance and Recovery of Micro, Small and Medium Enterprises of Georgia (National Bank Component) (WB) | 50,000 | 39,788 | 80%
25 07 01 05 | Rehabilitation of public schools in mountainous regions of Georgia and Development of energy efficiency (E5P, NEFCO) | 4,000 | 3,217 | 80%
24 14 01 05 | Open Program for the Energy Sector (Kfw) | 3,300 | 2,712 | 82%
26 09 - 31 06 03 - 31 06 04 | Irrigation and Land Market Development Project (WB) | 9,118 | 7,817 | 86%
24 14 01 04 | Strengthening of Guria Power Transmission Line Infrastructure (EU-NIF,KfW) | 15,850 | 13,615 | 86%
24 08 03 | Log-In Georgia (WB,EIB) | 50,000 | 43,130 | 86%
25 02 03 03 | East-West Express Highway Corridor Modernization-construction of the Samtredia-Grigoleti highway (EIB, EU) | 75,000 | 67,566 | 90%
27 04 02 03 | COVID-19 Vaccine Support Project in Asia-Pacific Vaccine Access (APVAX) (ADB) | 97 | 90 | 93%
27 04 03 | Georgia Municipal Infrastructure Renewal Project (EIB) | 20,903 | 19,604 | 94%
25 02 03 10 | Construction of Tbilisi-Bakurtsikhe-Lagodekhi road (ADB) | 30,000 | 28,513 | 95%
31 05 15 01 | Dairy Modernization and Market Access Program (DiMMA) (IFAD) | 11,000 | 10,518 | 96%
25 07 01 03 - 32 09 | Innovation, Inclusivity and Quality Project - Georgia I2Q ​​(WB) | 71,500 | 68,795 | 96%
25 05 03 | Integrated solid waste management program II (KfW) | 11,000 | 10,761 | 98%
25 05 02 | Kvemo Kartli Waste Management Project (SIDA, EBRD) | 1,500 | 1,470 | 98%
25 02 03 09 | North-South Corridor (Kvesheti-Kobi) Road (EBRD, ADB) | 185,000 | 182,503 | 99%
25 04 01 | Urban Service Improvement Program (Water Supply & Wastewater Sector) (ADB) | 47,000 | 47,232 | 100%
32 11 | Sector Loan for the Education Sector (ADB) | 2,500 | 2,600 | 104%
25 04 02 | Improvement of Communal infrastructure in Imereti and Kazbegi | 27,000 | 28,942 | 107%
24 14 01 03 | 500 kV OHL Jvari-Tskaltubo (WB) | 21,000 | 24,496 | 117%
25 02 03 01 | East-West Express Highway Corridor Improvement Project (Zemo Osiauri-Rikoti) (EIB, WB) | 75,000 | 87,687 | 117%
25 03 04 | Regional and Municipal Infrastructure Development Project II (WB, WB-TF) | 16,000 | 18,717 | 117%
56 13 01 | Solid Waste Project of Adjara (EBRD, SIDA) | 5,000 | 6,275 | 126%
25 02 03 07 | Reconstruction-construction of Ubisa-Shorapani section of Tbilisi-Senaki-Leselidze road (EIB) | 107,000 | 136,884 | 128%
25 02 03 06 | Reconstruction-construction of Ubisa-Shorapani section of Tbilisi-Senaki-Leselidze road (EIB) | 17,500 | 22,643 | 129%
24 12 - 25 03 05 - 56 13 04 | Livable Cities Investment Program (ADB) | 38,600 | 51,123 | 132%
25 02 03 02 - 25 02 03 11 | Batumi New Bypass Road Project (ADB, AIIB) and Construction of the Poti Bridge over the Rioni River (ADB) | 54,000 | 75,596 | 140%
56 13 10 | Tbilisi Bus Project (Phase II-Gas) (EBRD) | 200 | 354 | 177%
25 02 03 04 | Reconstruction-construction of Chumateleti-Khevi section of Tbilisi-Senaki-Leselidze road (WB, EIB) | 60,000 | 122,623 | 204%
56 13 05 | Sustainable urban mobility (KfW) | 800 | 1,663 | 208%
25 02 03 08 | Construction of Senaki-Poti-Sarpi road km48-km64 Grigoleti-Choloki section (EIB) | 17,000 | 35,772 | 210%
25 04 03 | Development of water supply and wastewater systems of the city of Khashuri and surrounding settlements (AFD, EU) | 10,600 | 26,618 | 251%
56 13 02 02 | Tbilisi Municipal Services Project (EBRD) | 5,000 | 21,957 | 439%
25 02 03 05 | Reconstruction-construction of Khevi-Ubisa section of Tbilisi-Senaki-Leselidze road (ADB) | 12,500 | 55,007 | 440%
32 10 | Professinoal Education Program 1 (KfW) | 0 | 15,316
25 02 02 10 | Batumi (Angisa) - Rehabilitation-Reconstruction of Khulo-Zarzma Section of Akhaltsikhe Highway (Kuwait Fund) | 0 | 1,005
25 04 07 | Sustainable Water Supply and Sanitation Sector Development Program (ADB) | 0 | 2,166
24 14 04 01 | 500 kV OHL "Ksani-Stefantsminda" (EBRD, EU, KfW) | 0 | 18,605
25 02 02 09 | Internal Road Asset Management Project (WB) | 0 | 137
25 02 02 11 | Rehabilitation and reconstruction of Chumateli-Kharagauli section of Durila-Kharagauli-Moliti-Pona-Chumateti internal road (ADB) | 0 | 18
25 03 06 | Bakuriani Municipal Services Improvement Program (EBRD) | 0 | 131
25 07 01 02 | Tbilisi Public School Rehabilitation and Energy Efficiency Project (CEB, E5P) | 0 | 409
56 13 02 03 | Tbilisi Waste Management Project (EBRD) | 0 | 655
56 13 02 04 | Tbilisi Landfill Gas Collection System Project (E5P, EBRD) | 0 | 469